BMTCI PROGRAM

Volume Impact Analysis

Prepared for American Red Cross (ARC) — Contract Review & Scope Expansion

In Collaboration with Centro Comprensivo de Cancer · Universidad de Puerto Rico

TCT Participation at CCCUPR Effective August 2026  |  Confidential

June 2026

01  ·  PURPOSE

This document demonstrates:

For ARC — The projected apheresis collection and cell processing volumes that the BMTCI Program at CCCUPR will generate under the ARC services agreement, justifying contract scope expansion to include autologous HSC collection, CAR-T lymphocyte apheresis, and allogeneic donor collections.

For Stakeholders — How TCT's participation at CCCUPR (effective August 2026) will redistribute hematologic oncology patient volumes across Puerto Rico's hospital landscape, retaining patients on-island who currently travel to the US mainland.

02  ·  PROGRAM OVERVIEW

The BMTCI Program (Hematopoietic Stem Cell Transplantation & Cellular Immunotherapy) launches at CCCUPR as a new department — peer to Medical Oncology and Surgical Oncology — under the Hospital Medical Director. TCT Oncology provides transplant/cellular therapy expertise in collaboration with the CCCUPR academic platform.

TCT Oncology Dual-Site Presence

TCT operates at both CCCUPR (BMTCI Program) and Auxilio Mutuo Hospital (HAM), where TCT has an established allogeneic HSCT program and CIBMTR reporting infrastructure. This creates a complementary referral network — CCCUPR handles auto-HCT and CAR-T, while allo-HSCT patients identified at CCCUPR are referred to HAM through TCT, increasing HAM's allogeneic volume.

| Phase | Timeline | Scope | Volume Target |
| --- | --- | --- | --- |
| Phase 1 | Year 1 (2026-2027) | Autologous HCT | 10-15 auto-HCTs |
| Phase 2 | Year 2-3 (2028-2029) | + CAR-T, donor search, HLA | 20-30+ transplants/yr |
| Phase 3 | Year 3+ (2029+) | + Allo HCT, gene therapy, FACT | Full-spectrum cellular therapy |

Infrastructure: 3-4 HEPA-filtered rooms, outpatient transplant clinic, 2-3 apheresis chairs, pharmacy BSH, ICU with CRS/neurotoxicity capability. Staffing: 18-22 FTE (Phase 1), 26-30 (Phase 2), 32-37 (Phase 3).

03  ·  PUERTO RICO HEMATOLOGIC MALIGNANCY BURDEN

Annual Disease Incidence

| Cancer Type | Incidence (per 100K) | Est. Cases/Year | Notes |
| --- | --- | --- | --- |
| Leukemia (all subtypes) | 10.2 | ~325 | 9th most common cancer in PR |
| Non-Hodgkin Lymphoma | ~13.5 | ~430 | 6th males, 7th females |
| Hodgkin Lymphoma | ~2.5 | ~80 | — |
| Multiple Myeloma | ~6.5 | ~210 | Increasing, younger women |
| Other (MDS, MPN) | ~2.0 | ~65 | — |
| Total | ~34.7 | ~1,110 |  |

Sources: PR Central Cancer Registry; SEER Program; Pop: 3,184,835 (US Census 2025)

Treatment-Eligible Patient Funnel

| Stage | Patients/Year | Notes |
| --- | --- | --- |
| New hematologic malignancies | ~1,110 | All subtypes |
| Auto SCT-eligible (MM, NHL, HD) | ~150-200 | Consolidation or salvage |
| Allo-HSCT eligible (AML, ALL, MDS) | ~40-60 | Requires matched donor |
| CAR-T eligible (2nd/3rd+ line) | ~80-120 | After >=1 prior line |
| Currently receiving auto SCT on-island | ~20-35 | HAM only |
| Currently receiving allo-HSCT on-island | ~8-15 | HAM only (limited) |
| Currently receiving CAR-T on-island | 0 | No program exists |
| Traveling to mainland US | ~60-100 | Those who can afford/access |
| Eligible but untreated (access gap) | ~70-120 | Cannot afford or access |

04  ·  ARC SERVICES — PROJECTED COLLECTION VOLUMES

The ARC contract must cover the following services for the BMTCI Program. These volumes represent new activity generated by the program — not redistribution of existing ARC workload.

| ARC Service | Year 1 (2027) | Year 2 (2028) | Year 3 (2029) | Year 5 (2031) |
| --- | --- | --- | --- | --- |
| Autologous HSC collections | 12-18 | 22-32 | 30-42 | 40-55 |
| CAR-T lymphocyte apheresis | 4-8 | 10-14 | 16-22 | 30-45 |
| Allo donor collections (HAM via TCT) | 4-6 | 8-12 | 10-15 | 15-22 |
| Cryopreservation events | 16-24 | 30-44 | 40-57 | 55-77 |
| Product release testing | 20-32 | 40-58 | 56-80 | 85-122 |
| Chain-of-custody/identity | 20-32 | 40-58 | 56-80 | 85-122 |
| Total apheresis procedures | 20-32 | 40-58 | 56-80 | 85-122 |

ARC Contract Scope Requirements

| Service Category | Status | Action Required |
| --- | --- | --- |
| Autologous HSC collection & processing | Confirm | Verify explicit coverage |
| HSC cryopreservation & storage | Confirm | Verify capacity & pricing |
| CAR-T lymphocyte apheresis & shipment | Likely gap | Amend contract for leukapheresis |
| Product release testing | Confirm | Verify turnaround times |
| Chain-of-identity / custody | Confirm | Must meet FACT-JACIE standards |
| Deviation reporting | Confirm | Align with CCCUPR quality program |
| Pricing & pass-through costs | Review | Negotiate volume-based pricing |
| Capacity & turnaround guarantees | Critical | SLA must guarantee emergent slots |
| Allo donor collections (Phase 3) | Not yet needed | Plan amendment by Year 2-3 |

05  ·  HOSPITAL VOLUME IMPACT

Baseline: Where Patients Go Today

| Hospital / Destination | Consults/Yr | Auto SCT | Allo-HSCT | CAR-T |
| --- | --- | --- | --- | --- |
| CCCUPR | 2,200-2,800 | 0 | 0 | 0 |
| Auxilio Mutuo (HAM) — TCT Oncology | 1,800-2,200 | 15-25 | 8-15 | 0 |
| HIMA San Pablo Oncologico | 1,500-1,800 | 5-10 | 0 | 0 |
| Other PR hospitals & practices | 2,400-3,400 | 0 | 0 | 0 |
| Mainland US | — | 40-60 | 20-30 | 30-50 |
| Access gap (never treated) | — | ~50-80 | ~12-15 | ~50-70 |
| Total eligible | ~8,000-10,200 | ~110-175 | ~40-60 | ~80-120 |

On-island treatment rates — Auto SCT: ~18-20%  |  Allo-HSCT: ~20-25%  |  CAR-T: 0%

Autologous SCT — Projected Cases Per Year

| Hospital | Baseline | Year 1 | Year 2 | Year 3 | Year 5 |
| --- | --- | --- | --- | --- | --- |
| CCCUPR / BMTCI Program | 0 | 10-15 | 22-30 | 30-40 | 40-50 |
| Auxilio Mutuo (HAM) — TCT | 15-25 | 13-22 | 12-20 | 10-18 | 10-15 |
| HIMA San Pablo | 5-10 | 5-10 | 8-12 | 10-15 | 12-18 |
| Mainland US | 40-60 | 30-45 | 22-35 | 15-25 | 8-15 |
| Access gap | 50-80 | 40-60 | 28-42 | 18-28 | 8-12 |
| Treated on-island | 20-35 | 28-47 | 42-62 | 50-73 | 62-83 |
| On-island capture rate | ~18-20% | ~29-31% | ~46-45% | ~60-58% | ~79-75% |

Allogeneic HSCT — HAM via TCT Oncology

TCT's dual-site presence creates a direct referral pipeline from CCCUPR to HAM for allo-HSCT. Patients identified at CCCUPR who require allogeneic transplant are referred to HAM through TCT — the only team performing allo-HSCT in Puerto Rico.

| Hospital | Baseline | Year 1 | Year 2 | Year 3 | Year 5 |
| --- | --- | --- | --- | --- | --- |
| Auxilio Mutuo (HAM) — TCT | 8-15 | 12-18 | 16-24 | 20-30 | 25-38 |
| CCCUPR / BMTCI Program | 0 | 0 | 0 | 0-2 | 3-8 |
| Mainland US | 20-30 | 16-25 | 12-20 | 10-16 | 6-10 |
| Access gap | 12-15 | 10-12 | 8-10 | 5-8 | 3-5 |
| HAM allo growth vs. baseline | — | +50-20% | +100-60% | +150-100% | +213-153% |

CCCUPR diagnoses ~15-25 allo-eligible patients/year who currently go to the mainland or go untreated. TCT at CCCUPR identifies these patients early and routes them to HAM.

CAR-T Infusions — Projected Cases Per Year

| Hospital | Baseline | Year 1 | Year 2 | Year 3 | Year 5 |
| --- | --- | --- | --- | --- | --- |
| CCCUPR / BMTCI Program | 0 | 4-8 | 10-14 | 16-22 | 30-45 |
| Auxilio Mutuo (HAM) | 0 | 0 | 0 | 0 | 0 |
| HIMA San Pablo | 0 | 0 | 0 | 0 | 0 |
| Mainland US | 30-50 | 25-42 | 22-36 | 18-28 | 10-16 |
| Access gap | 50-70 | 42-58 | 35-48 | 28-38 | 15-22 |
| Actually treated | 30-50 | 29-50 | 32-50 | 34-50 | 40-61 |
| Treatment access rate | ~38-42% | ~41-46% | ~48-51% | ~55-57% | ~73% |

Hematology/Oncology Consults Per Year

| Hospital | Baseline | Year 1 | Year 2 | Year 3 | Year 5 |
| --- | --- | --- | --- | --- | --- |
| CCCUPR (incl. BMTCI) | 2,200-2,800 | 2,500-3,200 | 2,700-3,400 | 2,900-3,600 | 3,200-3,900 |
| Auxilio Mutuo (HAM) — TCT | 1,800-2,200 | 1,850-2,250 | 1,900-2,300 | 1,950-2,350 | 2,000-2,400 |
| HIMA San Pablo | 1,500-1,800 | 1,500-1,800 | 1,500-1,800 | 1,500-1,800 | 1,500-1,800 |
| Other PR hospitals | 2,400-3,400 | 2,350-3,350 | 2,300-3,300 | 2,300-3,300 | 2,300-3,300 |

Both CCCUPR and HAM consult volumes increase. The TCT dual-site model is additive, not competitive.

06  ·  NET IMPACT ON EACH HOSPITAL

| Hospital | Auto SCT | Allo-HSCT | CAR-T | Consults | Net |
| --- | --- | --- | --- | --- | --- |
| CCCUPR | +10-50/yr | 0 to 0-8 | +4-45/yr | +300-1,100 | Strong positive |
| HAM — TCT | -2 to -10 | +4 to +23 | No change | +50-200 | Net positive |
| HIMA San Pablo | Minimal | No change | No change | Stable | Neutral |
| Other PR | No change | No change | No change | -50 to -100 | Minimal |
| Mainland US | -10 to -45 | -6 to -20 | -5 to -34 | — | Significant reduction |
| Access gap | -10 to -68 | -4 to -10 | -8 to -48 | — | Major positive |

Auxilio Mutuo (HAM) — Detailed Impact via TCT Oncology

TCT's dual-site model makes HAM a net beneficiary of the BMTCI Program at CCCUPR:

| HAM Metric | Baseline | Year 5 (2031) | Change |
| --- | --- | --- | --- |
| Auto SCT cases/year | 15-25 | 10-15 | -5 to -10 (mild decline) |
| Allo-HSCT cases/year | 8-15 | 25-38 | +17 to +23 (significant growth) |
| Total transplants/year | 23-40 | 35-53 | +12 to +13 net gain |
| Hem/onc consults/year | 1,800-2,200 | 2,000-2,400 | +200 (allo workups) |
| CIBMTR reportable cases | 23-40 | 35-53 | +52-33% increase |

The allo-HSCT growth alone more than compensates for any auto SCT volume shift. HAM's transplant program becomes larger and more complex — strengthening its FACT credentials and academic profile.

07  ·  KEY TAKEAWAY

The BMTCI Program at CCCUPR does not cannibalize existing Puerto Rico hospital programs.

The overwhelming majority of volume comes from three sources:

CCCUPR's own patients — patients who currently have no on-site transplant option

Mainland repatriation — patients kept on-island instead of traveling to the mainland

Access gap recovery — patients who would never have been treated

Transformation of Puerto Rico's Cellular Therapy Landscape

| Metric | Today | Year 5 (2031) | Change |
| --- | --- | --- | --- |
| On-island auto SCT/year | 20-35 | 62-83 | +210-137% |
| On-island allo-HSCT (HAM via TCT) | 8-15 | 25-38 | +213-153% |
| On-island CAR-T/year | 0 | 30-45 | From zero |
| Total on-island transplants + CAR-T | 28-50 | 117-166 | +318-232% |
| On-island capture (auto SCT) | 18-20% | 75-79% | +57 pts |
| On-island capture (allo-HSCT) | 20-25% | 68-62% | +43 pts |
| Treatment access (CAR-T) | 38-42% | 73% | +33 pts |
| Patients traveling to mainland | 60-100/yr | 18-31/yr | -70% |
| Eligible untreated | 120-150/yr | 23-34/yr | -78% |
| HAM total transplant volume | 23-40/yr | 35-53/yr | +52-33% |
| ARC apheresis procedures/year | 0 | 85-122 | New volume |

For ARC

This represents a sustained, growing volume of apheresis collections and cell processing services — starting at 20-32 procedures in Year 1 and scaling to 85-122 procedures by Year 5. This includes auto HSC collections (CCCUPR), CAR-T leukapheresis (CCCUPR), and allo donor collections (HAM via TCT). This is entirely new programmatic volume.

For HAM

TCT's dual-site model drives a net increase in HAM's total transplant volume (+52-33% by Year 5). The mild decline in auto SCT (-5 to -10 cases) is more than offset by allo-HSCT growth (+17 to +23 cases) generated by CCCUPR referrals through TCT.

Prepared for BMTCI Program stakeholders and American Red Cross contract review

Carlos Mendez, COO — cmendez@tctoncology.com

June 2026  |  Confidential